## Instructions
MGB Timeline/Template for Grant Proposal Submissions Version 01.00.01
Date proposal due to immediate sponsor (funding agency or prime site if subcontract): | Grant Administrator | 1 | 2021-03-05
Action |  | 2 | Latest Date Due | 3 Departmental Timelines
Email to Department Grants Administrator that you are thinking of submitting a proposal |  | x | 2021-01-08 | 3 8 weeks before deadline
Meet with Grants Admin staff to draft budget and distribute tasks | x | x | 2021-01-22 | 6 weeks before deadline
Provide title, project period, list of key personnel and whether or not human subjects are involved (so that Insight record can be established) |  | x 4 | 2021-01-22 | 6 weeks before deadline
Request paperwork from subcontract sites; request letters from consultants and other LOS. Set the date paperwork is due to you for at least 14-16 business days before proposal is due. |  |  | 2021-01-22 |  | 5
If Single IRB applies, determine which site will serve; if MGH complete and submit budget template to IRB for approval. |  |  | 2021-01-22
Finalize MGH budget and justification | x | x | 2021-02-05 | 4 weeks before deadline
Subcontractors and consultants to have their signed complete documents to MGB (PI or admin) |  |  | 2021-02-09 | 18 Business days before deadline
Administrative Component due to Research Management approval and submission (staff/admin submits) | x | x | 2021-02-24 | 8 Business days from Sponsor Due Date
Final (Science) Components due for Research Management and submission and ready for upload to Assist (staff/admin submits) | x | x | 2021-03-03 | 3 Business days before deadline
(Note: this is a general list- consult the Program Announcement for your submission for details)
Documents Required for Proposal Submission
5. Formula in Formula Bar =WORKDAY(D3,-30,holidays)
6. =WORKDAY means the formula will exclude Saturday & Sunday
8. Formula in Formula Bar
=WORKDAY(D3,-30,holidays)
To change the number of days required by your department (in any formula field) just change the number in the formula to the numbers of days you require preceded by a negative sign.
2. .Latest Due Dates column will automatically populate based on the Due Date/formulas 22.
1. Insert the Sponsor Due Date
3. .Departments can set their own timelines22.
4. .Departments can change the formula to match their timelines. Click in cell to see the formula.
7. (D3,-30,holidays)
D3 = Sponsor Due Date (Cell D3)
-30 is the number of days needed at department (6 weeks X 5 days a week =30) business days before deadline)
holidays means the formula will exclude the holidays listed in the holiday chart

## Template
MGB Timeline/Template for Grant Proposal Submissions Version 01.00.00
Date proposal due to immediate sponsor (funding agency or prime site if subcontract): | Grant Administrator | PI | 2024-02-05 |  | 2023-24 Holidays excluded:
Action |  |  | Latest Date Due | Time frame (note: earlier is always better) | Christmas Day 2022 (Recognized) | 2023-12-25
Request Form & Mandatory Questionnaires due to submit. (So that the INSIGHT & ASSIST records can be established) |  | x | 2023-12-20 | 6 weeks before deadline | New Years day (Recognized) | 2024-01-01
IF you have a subcontract/s listed on your budget: Request paperwork from subcontract sites; request letters from consultants and other LOS. The paperwork is due at least 14-16 business days before proposal is due. | x | x | 2023-12-20 | 6 weeks before deadline | MLK Day | 2024-01-15
Administrative Components are due to Grant Administrator with the FINAL MGH budget and justification (Download the appropriate forms from Checklist) |  | x | 2024-01-08 | 20 business days before deadline | Presidents Day | 2024-02-19
The grant administrator assigned to your proposal will review all admin documents and start processing, the record will be routed to RM through the internal routing system for review by our signing official |  |  | 2024-01-16 | 15 Business days before deadline | Memorial Day | 2024-05-27
Research Management Administrative Component Deadline |  |  | 2024-01-25 | 8 Business days from Sponsor due date | Juneteenth | 2025-06-19
Final Science Component due to Grant Administrator to upload in ASSIST System and prepare it for Final submission | x | x | 2024-01-31 | 4 Business days before deadline | July 4th | 2024-07-04
Subcontractors and consultants to have their signed complete documents to MGB (PI or DA) |  |  | 2024-02-01 | 3 Business days before deadline | Labor Day | 2024-09-04
Please download the Required Documents for the Proposal from the Check List Link |  |  |  |  | Indigenous People | 2024-10-10
[5 empty] | Thanksgiving | 2024-11-28
[5 empty] | Xmas | 2024-12-25
[5 empty] | New Years Day | 2025-01-01
[5 empty] | MLK Day | 2025-01-18
[5 empty] | Presidents Day | 2025-02-17
[5 empty] | Memorial Day | 2025-05-26
[5 empty] | Juneteenth | 2025-06-19
[5 empty] | Fourth of July | 2025-07-04
[5 empty] | Labor Day | 2025-09-01
[5 empty] | Indigenous People | 2025-10-13
[5 empty] | Thanksgiving | 2025-11-27
[5 empty] | Xmas | 2025-12-25
V1 March 11/2021